## Suggested 12 month Action Plan
SEA Alliance 12 Month Action Plan (Jan-Dec 2020). Updated October 2020.
Area of work/objective | SEA Alliance Action(s) | Lead SEA Alliance member/person | Partners/complementary initiatives | Delivery date | Output/Status
1. Information gathering and risk assessment | 1.1. Agree a common set of social data points that should be collected as part of human rights due diligence, in line with PAS 1550 and Global Dialogue on Seafood Traceability (GDST). To support 1.2. | Andy Hickman | GDST/WWF/Others | Feb 2020 Nov 2020 | Discussions are ongoing around a systemised approach and alignment on an agreed risk assessment framework/criteria. Will follow 1.2.
| 1.2. Informed by 1.1 undertake human rights assessment of key source fisheries, using publicly available information, outcomes of SEDEX Vessel Questionnaire, and other sources of information (Note: this proposed action will be reflected in the 1 pager on the SEDEX Vessel Questionnaire). | Joe Prosho Andy Hickman | Seafish Seafood Slavery Risk Tool (SSRT) FishWise | Feb 2019 Feb 2020 Mar 2020 Mar 2020 May/June 2020 July 2020 Sept 2020 Nov 2020 | Sedex was first mentioned to the SEA Alliance participants. Only 40 questionnaire completed as at Jan 2020. Sedex. Need to re-introduce and encourage more engagement. Will be re-introduced later. Seafish country profiles published. List of UK source fisheries circulated 03/2020. Explored how to conduct a high-level risk assessment of the SFP/ODP list. New SSRT to be presented to SEA Alliance. Appointed consultant and commenced risk assessment work. First draft completed. Under review.
| 1.3. Carry out pilots of PAS 1550 and create simplified implementation guidance | Mike Mitchell, Lucy Blow, Karen Green | SFP | April 2019 April 2020 June 2020 June 2020 Aug - Oct 2020 Oct 2020 | SEA Alliance PAS Working Group formed. Working with NGO coalition. ToR produced. First draft of the guidance produced. Call with OceanMind re collaboration. Next steps agreed. Collaboration between SEAA SG and NGO authors. Final draft of implementaion guidance produced.
2. Enhanced due diligence | 2.1. Consider how SEA Alliance members could work collaboratively to produce deeper dive intelligence on areas of concern. | Andy Hickman |  | Feb 2020 Nov 2020 | Looking to produce a ToR to support this work. This will follow the risk assessment work above.
| 2.2. Full safety and security measures for all fisheries observers in light of recent media reports | Andy Hickman/Karen Green | Human Rights at Sea Global Tuna Alliance | Sept - Oct 2020 | Full analysis of the issue. Report produced. Awaiting news of MSC research funding in this area.
| 2.2. Feed into and review outcomes of "UK Fisheries Human Rights and Social Welfare baseline needs assessment" being carried out by Human Rights at Sea | Decision will follow after the outcomes of this baseline assessment are known. | Human Rights at Sea | Apr 2020 | COVID-19 has delayed progress on this.
3. Improving fisheries and supply chain | 3.1. If human rights assessment identifies need, develop common Code of Practice, containing SEA Alliance interested parties' expectations for human rights standards in the fishing sector | NESI and Joe Prosho | FAO |  | This work has been delayed by the FAO.
| 3.2. Support development and deployment of effective grievance mechanism for the fishing sector | Andy Hickman | Global Seafood Assurances | Feb 2020 Apr 2020 June 2020 Nov 2020 | Looking for more information. Collaborative conversations. Details of funded-proposal circulated. Workshop for SEA Alliance planned.
| 3.3. Formalise and publicise SEA Alliance commitment to Employer Pays Principle for recruitment of workers in fishing sector |  | Leadership Group for Responsible Recruitment |  | Statement to be produced.
4. Advocacy and engagement | 4.1. Look at initiatives where SEA Alliance could engage. 4.1.1. Participate in Technical Advisory Committee of the Responsible Fishing Scheme now Responsible Fishing Vessel Standard. | Sam Ludlow-Taylor | Global Seafood Assurances | Feb 2020 April 2020 June 2020 | Estelle Brennan has joined GLP Working Committee in Thailand. Discussions with RFVS team in April 2020. New structure in place from May 2020. Estelle Brennan will be on new GSA Standards Oversight Committee.
| 4.2. Engage with MSC to review (and strengthen where applicable) social elements of MSC Fisheries Standard | Andy Hickman/Karen Green | MSC | Feb 2020 Apr 2020 May 2020 July 2020 Oct 2020 Oct 2020 | Letter drafted and sent to MSC. Follow up call with MSC with continued engagement planned. Urged participants to respond to FisheryProgress consultation. Urged participants to respond to SSCI/GSSI consultation. Follow up FisheryProgress workshop. Urged participants to respond to 2nd FisheryProgress consultation.
| 4.3. Develop advocacy strategy prioritising source countries that have not ratified/implemented key international standards. SEA Alliance to endorse activites where appropriate. | BRC/SIA to lead on advocacy. | EJF, ETI, BRC | Sept 2019 Feb 2020 Oct 2020 Oct 2020 | UK Seafood Industry letter to the Royal Thai Government with support for Thailand to ratify ILO Conventions. Oxfam Thai Government Advocacy letter to support the continuation of the fishery reforms in Thailand. SG meeting with Oxfam. EU-Thai Trade Agreement letter.
| 4.4. UK fishing fleet transit visa regime. | William Davies/Andy Hickman/Karen Green | FWA/SWFPA | Sept - Oct 2020 Nov 2020 | Engagement with catching sector to see how SEA Alliance could support measures to improve the current system. This is ongoing
| 4.5. Hold side event at UN Committee on Fisheries to engage key stakeholders. Create momentum for what the SEA Alliance is doing - speaking opportunities. | Steering Group | Seafood events |  | On hold due to COVID-19
5. Monitoring Progress and Impact | 5.1. Monthly Steering Group calls to review progress and identify key next steps | Karen Green |  | 2020 | Scheduled every month throughout 2020.
| 5.2. 2 x in person SEA Alliance Meetings during 2020 | Karen Green |  | Jan 2020 July 2020 Oct 2020 Nov 2020 Nov 2020 | Held on 28 January 2020 at Fishmongers' Hall. Online meeting 14 July 2020 with SSRT workshop. Workshop on FisheryProgress social policy Workshop on GSA worker voice project planned Workshop on funding application planned
| 5.3. 2 x in person half day planning meetings for SEA Alliance Steering Group | Karen Green |  | On hold | Not planned due to COVID-19.
| 5.4. Independent evaluation of 2020 Action Plan | Andy Hickman |  | Dec 2020 | To wait until the end of 2020.
| 5.5. Funding opportunity | Andy Hickman | Packard Foundation | Nov 2020 | Meeting scheduled

## Sheet1
SEA ALLIANCE WORKPLAN TO DELIVER THE SEA ALLIANCE FRAMEWORK
SEA Alliance Vision – what we aim to achieve:
The SEA Alliance will aim to deliver best practice solutions to identified, defined, and prioritised, ethical and welfare seafood issues affecting the UK & Ireland seafood sectors, including international and domestic supply chains. The SEA Alliance will build on the experience of participants in order to generate positive action and appropriate advocacy to improve working environments for seafood workers.
Working Framework – how we plan to do this:
SEA Alliance participants will work collaboratively to provide assurance of legal and responsible practices in our supply chains, and where we perceive the need, we will actively seek to improve standards. We will do this in two ways: A). By improving our knowledge and assisting and advising in the development of supply chain tools; B). by advocating for improved workplace conditions and listening to the worker voice through our member activities. The workplan below aims to deliver these two goals by the following means:
Aim | Key Outcome required | Actions: SEA Alliance WORKSTREAMS | Actions: SEA Alliance will ADVOCATE FOR and SUPPORT other organisations to deliver: | Considerations | Who else is working in this space? | SEA Alliance deliverables | Timeframe
1. Information gathering: to build our collective understanding of governance and regulations, government monitoring and conformance with international standards (e.g. ILO) as a credible and authoritative baseline to contribute to risk assessment and inform advocacy priorities. | A common set of reference materials that SEA Alliance members (and their supply chains?) can use to better understand governance and regulations, and conformance to international human rights standards. | AH: Might there be an opportunity for us to work together to define "what good looks like" for the MSC statements outlining the measures the fishery clients have in place to mitigate forced or child labour? | Undertake a desk-based review to collect information on applicable regulations, standards and levels of compliance in different parts of the fishing industry. AH: How does this link to the work being done by Veris Maplecroft on behalf of Seafish? | This could draw on information from the ILO, US State Department, NGOs etc. (much info out there, not organised in a manner specifically for SEA Alliance aims. E.g. Info can be by company, or country, or fishery (and will need compliance across all ultimately). We're trying to tackle human trafficking and forced labour through traditional social compliance methods like RFS - need to separate slavery issues from working conditions i.e. what is the best approach to identify and address human trafficking/labour abuse versus the right way to assess /address day to day working conditions. | Information on applicable regulations, standards and levels of compliance in different parts of the fishing industry are already beng worked on by various groups.
|  | Agree a suite of key instruments (per above) that all SEA Alliance members should understand and work towards compliance with. |  | Could use a SEA Alliance Code of Practice amongst those instruments (see below in 3.). Also note many nations not yet compliant to eg ILO 188. | This links with the FAO Draft Guidance. | A SEA Alliance/EJF and WWF joint working group has been formed to develop a PAS 1550:2017 Code of Practice implementation guide
|  | Share this knowledge (desk-based review) and the materials with SEA Alliance members, supply chains and other interested parties. |  | 1. Outreach materials and methods need to be supply-chain-appropriate, may require expertise to develop. 2. FAO are developing a Code of Conduct for Responsible Labour practice in aquaculture and fisheries (also CGF SSCI/ GSSI benchmark) is progressing. Is developing our own UK industry common approach possibly the right way to go? | FAO has just consulted on its Draft Guidance on Social Responsibility in Fisheries and Aquaculture Value Chains. July 2019. It is not clear how the GSSI/CGF Benchmark is progressing.
2. Risk Analysis: to collaborate in the development and deployment of risk assessment tools – agreeing common frameworks for collecting supply chain information and engaging in joint research/analysis where possible (e.g. Human Rights Risk Assessments). | A UK-market-shared common means to mitigate human rights issues, including through common tools for outreach, education, advocacy, presentation, so that all supply chains see a "UK market common approach" to human rights. |  | Review existing risk assessment tools (e.g. public, by specialist consultancies, and/or in house) and agree which of those will be useful to the SEA Alliance. Include assessment of worker voice - what's available and what's effective | i. Important to include workers voice in risk analyses. Ii. Risk analysis data needs to produce common outcomes (anonymised if necessary to observe commercial IP /competition law ). | The Seafish Social Risk Assessment Information spreadsheet has just been completed and sent to the SEA Alliance SG for comments. Worker voice is not a key area.
|  | Where necessary, agree a common framework for collecting supply chain information (suitable to collate/identify common geographies/ fisheries/ issues). |  |  |  | Engaged with the Fishing Vessel Labour Practices Data Collection: A collaborative pilot project between the Seafood Ethics Action Alliance (SEA Alliance) and Sedex.
Undertake risk-assessment to prioritise key issues/geographies and/or fisheries, where collaborative action is needed. Undertake specific Human Rights Impact Assessments where necessary. AH: Interesting to note that Human Rights at Sea will be doing a "UK Fisheries Human Rights and Social Welfare baseline needs assessment."
3. Engaging standards: to collaborate in the support, recognition and deployment of a suite of benchmarked independent standards, and where necessary offering developmental advice. AH: When we say "suite" it sounds like we are aiming for a variety of standards - should we be promoting a smaller number of standards for simplicity? | A common set of independent standards used by SEA Alliance members to 3rd party assess their supply chains' against human rights risks. (AH: Should this section specifically reference RFS, MSC and any other relevant standards?) |  | Identify relevant standards (existing or in development) that have social standards/human rights in scope. | There are a limited no. of standards in existence (mostly aqua) and some being developed that SEA Alliance may wish to support. | This is the area GSSI and CGF are focussing on.
Support the development/improvement of those standards to better address human rights risks.
|  | Consider the development of a common Code of Practice, containing expectations for human rights standards in the fishing sector. AH: It would be good to consider how this could build on other tools e.g. the Seafood Task Force auditable standard, the FAO Code of Practice etc. |  | NB FAO Code of Conduct being developed as mentioned above.
4. Promoting transparency and traceability: improving supply chain transparency through the acknowledgement and deployment of social KDEs. AH: Content of this section focuses on traceability rather than transparency, and one specific element of traceability - the use of conmmon KDEs. Perhaps it would be useful for us to look at content of EJF Transparency Principles, which a number of us have signed up to. https://ejfoundation.org/resources/downloads/EJF-Transparency-10-principles-final-1.pdf | Develop and utilise agreed set of social KDEs across SEA Alliance members' supply chains using them to identify risks, educate, promote improvements. | We see traceability as a physical recording system from sea to retailer which will be a paper/electronic data capture system. We could engage with the Global Dialogue on Seafood Traceability (GDST) to help inform the development of social Key Data Elements (KDEs). |  | AH: It would be good to understand exactly where the GDST process for defining social KDEs has got to. It has been going on for a really long time.
Work towards building social KDEs into supply chain information systems.
Engage with other actors/initiatives promoting fisheries transparency e.g. SALT, EJF, WWF etc.
5. Promoting positive change at a fishery level: working together to drive improved standards in priority source fisheries through engagement with suppliers, fishers and relevant NGOs/Unions. | A model for collaborative action at a fishery level akin to a Fishery Improvement Project (FIP). | Consider the development of a common Code of Practice, containing SEA Alliance interested parties' expectations for human rights standards in the fishing sector. AH: I feel this would be a very positive step, but it would be best to be fairly high-level, so as not to exclude any fisheries with particular characteristics. |  | A common code supports the SEA Alliance aims to work collaboratively, use best practice solutions, and using common tools to communicate them. AH: To what extent can the FAO Guidance document play the role of "common code"?
Collaboratively review, recommend to and adopt appropriate materials that can help to engage suppliers/fishers.
|  | Work with the supply chain to develop and implement an improvement plan (e.g. to improve recruitment practices or vessel standards). And, where relevant, collaborate to support appropriate remediation (see note in column F). AH: It would be great to have some case studies of how this has been successfully done. |  | Requires experts. Complexities in fishing that you don’t find land-based e.g. if suspect criminality who to turn to when distant global waters? Quite complex. Interpol? Government agencies? Who are the right authorities and how to contact them, get the right advice, they much better placed to address than we are. Remediation - huge work area. What to do when issues arise incl issues of worker safety. Who provides and who funds? How to deal with corruption and criminality?
6. Influencing: recognising the limitations in how far corporate actions may have influence. SEA Alliance participants will also actively seek to influence national governments in the adoption and effective implementation of regulations for achieving and maintaining good labour standards. AH: How about really targeting the 2020 UN Committee on Fisheries (13-17th July), to set out a clear, positive narrative to Governments? | Effective engagement with key Governments to overcome key governance/policy challenges. | Work with experts to identify key governance/policy challenges in SEA Alliance member supply chains. | Is there a tangible role for the SEA Alliance members, and the Steering Group in particular, becoming an expert collective voice for the seafood supply chain ie with the FWA; the RFS Oversight Board; FishWise; CGF/GSSI? | Understanding relevant governments' approaches - important - thorny issues - how do we hold governments to account? Who/which authority can/does? |  | This is happening. The SEA Alliance is engaged directly or indirectly with the FWA; the RFS Oversight Board; FishWise; CGF/GSSI.
|  | Identify priority issues to address through advocacy. AH: This helpfully overlaps with EJF Transparency Principles. |  | Capacity - possibly a big issue for SEA Alliance: Slavery/human rights = global scale, crucial issues, needs to be dealt with urgently. Is each of us doing a bit more in our day job necessarily going to do it justice? - work streams need inbuilt capacity plans. AH: I think this is a good point. wE need to continually review whether we have the resource to deliver on our strategy/action plan. | AH: It's going to be key to identify partners in this element - just speaking as UK retailers/brands/suppliers, we may struggle to gain traction. | Letter to Thai Government urging ratification of ILO 188.
|  | Develop an advocacy strategy and action plan that reflects identified priorities. |  | One of the areas that requires quite experienced parties - understand the sensitivities - do we currently have this capacity in the SEA Alliance - who do we need to help us with this kind of work - some kind of human rights consultant?